## Sheet1
NIGERCO NIGERIA LIMITED OPERATIONS DEPARTMENTAL PLAN FOR YEAR 2014
MONTH | WEEK | SECTOR | TASK | OBJECTIVE | DURATION
[5 empty] | START | FINISH
MAY TO AUGUST | 16wks | OIL & GAS | Comprehensive review of the previous Quarter outstanding Operations in the Oil & Gas | 1. To note all terminals, depots & Jetties yet to be visited.
2. To ensure further implementations in the visited Oil & Gas Depot/Jetty inspection i.e Bills
3. To note the stage of Legal Metrology Implementation in the Oil & Gas Upstream
4. To Further discuss the modalities for the implementation of Legal Metrology in Nigeria
5. To Further discuss the modalities for the implementation of Legal Metrology in Nigeria
To complete the initial stage of the Oil & Gas Terminal inspection/Data collation and the commencement of the Verification exercise
To complete the initial stage of the Oil & Gas Downstream inspection/Data collation and the commencement of the Verification exercise
To complete the initial stage of the Oil & Gas Midstream inspection/Data collation and the commencement of the Verification exercise
|  |  | Schedule of Inspection in Midstream (Refineries that are yet to be Visited) and Downstream (Depots/Jetties that are yet to be visited). | To complete the initial stage of the Oil & Gas Downstream inspection/Data collation and the commencement of the Verification exercise
To complete the initial stage of the Oil & Gas Midstream inspection/Data collation and the commencement of the Verification exercise
|  |  | Inspection of the Scheduled Oil and Gas Upstream Terminal, Midstream and Downstream. | Completion of the Oil & Gas Upstream Terminal Inspection and Data Collation
To collate Datas of all metering instruments use for trade on the Midstream and Down Stream facilities
Schedule of Meetings
|  |  | 1. OPTS | To Further discuss the modalities for the implementation of Legal Metrology in Nigeria
|  |  | 2. Non-OPTS | To Further discuss the modalities for the implementation of Legal Metrology in Nigeria
|  |  | 3. DAPMAN | 1. To Enlighten the Downstream body on the implementations of Legal Metrology
|  | BANKING | Comprehensive review of last Quarter activities in the Banking Sector | To propel the Operations Department for next Verification exercise
|  |  | Schedule of Verification exercise on the ATMs, Note Counting and Bulk Note Counting Machine in the Banking Sector. | To achieve a scheduled operational plan for the implementation of Legal Metrology in the Banking sector (Verification exercise)
|  |  | Commencement of the Verification exercise of the ATMs, Note Counting and Bulk Note Counting Machines in the Banking Sector | To ensure accuracy and Compliance with WMD Act
|  | ELECTRICITY | Review of last Quarter activities in the electricity sector | To obtain the list of intending ISPs and also to Obtain all Correspondences made in the electricity sector thus far
|  |  | Schedule of Verification exercise in the Electricity Sector | To achieve a scheduled operational plan for the implementation of Legal Metrology in the Electricity sector (Verification exercise)
|  |  | Verification exercise of all metering instruments use for trade in the Electricity Sector | To ensure accuracy and Compliance with WMD Act
|  | MANUFACTURING | A Comprehensive Review of Last Quarter activities in the Manufacturing Sector of the economy | To obtain all correspondences in the Manufacturing Sector on the upcoming verification exercise.
|  |  | Schedule of Verification exercise of all Weighing & Measuring Instruments in the Manufacturing sector of the Economy. | To achieve a scheduled operational plan for the implementation of Legal Metrology in the Manufacturing sector of the Nigeria economy(Verification exercise) for the second Quarter
|  |  | Verification exercise of all Weighing and Measuring instruments in the Manufacturing Sector of the economy. | To ensure accuracy and Compliance with WMD Act
|  | ELECTRICITY | Review of last years activities in the electricity sector | To obtain the list of intending ISPs and also to Obtain all Correspondences made in the electricity sector thus far
|  | MANUFACTURING | A Comprehensive Review of Last year activities in the Manufacturing Sector of the economy | To obtain all correspondences in the Manufacturing Sector on the upcoming verification exercise.
| 2 | Oil & Gas | Schedule of Meetings
|  |  | 1. OPTS | To Further discuss the modalities for the implementation of Legal Metrology in Nigeria
|  |  | 2. Non-OPTS | To Further discuss the modalities for the implementation of Legal Metrology in Nigeria
|  |  | 3. DAPMAN | 1. To Enlighten the Downstream body on the implementations of Legal Metrology
2. To Further discuss the modalities for the implementation of Legal Metrology in Nigeria
|  |  | WMD/NNL Operations Meeting | 1. To discuss the Operational analysis thus far on the Legal Metrology Implementation. | As Scheduled
2. To delibrate further on the Modalities and new ideas on Legal Metrology Implementation
BANKING
FEBRUARY |  |  | Correspondences with the Banks on the upcoming Verification exercise | To ensure all proper Correspondences have been made prior to the Commencement of the verification exercise
|  | ELECTRICITY | Meeting with the Gencos and Disco on the implementation of Legal Metrology in Nigeria | To delibrate on the implementation of Legal Metrology in the Electricity Sector of the Nigeria economy
|  |  | Schedule of Verification exercise in the Electricity Sector | To achieve a scheduled operational plan for the implementation of Legal Metrology in the Electricity sector (Verification exercise)
|  |  | Correspondences with the Gencos and Disco on the upcoming Verification exercise | To ensure that all Communications has been made prior to the Verification exercise
|  | MANUFACTURING | Correspondences with the Manufacturing Companies | To enssure all proper Correspondence have been made prior to the commencement of Verification exercise
|  |  | Schedule of Verification exercise of all Weighing & Measuring Instruments in the Manufacturing sector of the Economy. | To achieve a scheduled operational plan for the implementation of Legal Metrology in the Manufacturing sector of the Nigeria economy(Verification exercise)
| 3 | Oil & Gas | Schedule of Inspection | Verification exercise
|  |  | 1. Upstream (Terminals which are yet to be visited). | To complete the initial stage of the Oil & Gas Terminal inspection/Data collation and the commencement of the Verification exercise
|  |  | 2.Downstream (Depots & Jetties which are yet to be visited). | To complete the initial stage of the Oil & Gas Downstream inspection/Data collation and the commencement of the Verification exercise
|  |  | 3. Midstream (Refineries that are yet to be visited). | To complete the initial stage of the Oil & Gas Midstream inspection/Data collation and the commencement of the Verification exercise
BANKING
|  |  | Monthly Operations report | To delibrate on the activities of the Operations Department
|  | ELECTRICITY | Verification exercise of all metering instruments use for trade in the Electricity Sector | To ensure accuracy and Compliance with WMD Act
|  |  | Monthly Operations technical report Writing | To ensure Proper documentation of Field experience
To Offer technical and procedural advice base on the experience
|  | MANUFACTURING | Commencement of Verification exercise of all Weighing and Measuring instruments in the Manufacturing Sector of the economy. | To ensure accuracy and Compliance with WMD Act
| 4 | OIL & GAS | Inspection of the Scheduled Oil and Gas Upstream Terminal | Completion of the Oil & Gas Upstream Terminal Inspection and Data Collation | As Scheduled
|  |  | Monthly Operations Technical Report writing | To ensure Proper documentation of Field experience
To Offer technical and procedural advice base on the experience
|  | BANK | Continuation of the Verification exercise of the ATMs, Note Counting and Bulk Niote Counting Machines. | To ensure accuracy and Compliance with WMD Act
|  |  | Monthly Operations report | To delibrate on the activities of the Operations Department
|  | ELECTRICITY | Verification exercise of all metering instruments use for trade in the Electricity Sector | To ensure accuracy and Compliance with WMD Act
|  | MANUFACTURING | Continuation of Verification exercise of all Weighing and Measuring instruments in the Manufacturing Sector of the economy. | To ensure accuracy and Compliance with WMD Act
| 1 | OIL & GAS | Monthly Operations Meeting | To sustained effort from inception and planning, through turnover and operation, to assure Successful delivery of the ongoing implementation of Legal Metrology in Nigeria
To Evaluate the Success of Operations Objective in meeting the Organisation goals.
|  |  | Monthly Operations Meeting with the WMD | To have a look on the activities of the Month and further delibrate on the upcoming activities for the new Month | As Scheduled
|  | BANKING | Same Above | Same above
|  | ELECTRICITY | Same Above | Same above
|  | MANUFACTURING | same Above | same above
| 2 | OIL & GAS | Midstream and Downstream Metering equipment inspection/Data collation | To collate Datas of all metering instruments use for trade on the Midstream and Down Stream facilities
|  |  | OPTS/ Non OPTS Technical Committee meeting | To further delibrate on the implementation of Legal Meetrology in the Oil and Gas Sector of the Ngeria economy
|  | BANKING | Schedule of Verification exercise on the ATMs, Note Counting and Bulk Note Counting Machine in the Banking Sector. | To achieve a scheduled operational plan for the implementation of Legal Metrology in the Banking sector (Verification exercise)
|  |  | Correspondences with the Banks on the upcoming Verification exercise | To ensure all proper Correspondences have been made prior to the Commencement of the verification exercise
|  | ELECTRICITY | Monthly Operation s Meeting | To delibrate on the activities of the Operations Department
|  |  | Monthly Operations Meeting with the WMD | To delibrate on the activities thus far and modalities of the upcoming activities
|  | MANUFACTURING | Monthly Operations Meeting
| 3 | OIL & GAS | Midstream and Downstream Metering equipment inspection/Data collation | To collate Datas of all metering instruments use for trade on the facilities
|  | BANKING | Verification exercise of the ATMs, Note Counting and Bulk Niote Counting Machines. | To ensure accuracy and Compliance with WMD Act
|  | ELECTRICITY | Verification exercise of all metering instruments use for trade in the Electricity Sector | To ensure accuracy and Compliance with WMD Act
|  |  | Monthly Operations technical report Writing | To ensure Proper documentation of Field experience
To Offer technical and procedural advice base on the experience
|  | MANUFACTURING | Schedule of Verification exercise of all Weighing & Measuring Instruments in the Manufacturing sector of the Economy. | To achieve a scheduled operational plan for the implementation of Legal Metrology in the Manufacturing sector of the Nigeria economy(Verification exercise)
| 4 | OIL & GAS | Monthly Operations Technical Report Writing | Updating the company on the status of the task and achievements of the Operations Department for the Month of February
|  |  | ISP Meeting (Operations) | Discussion on the information and Data collated from the Oil and Gas Terminals, Depots , Jetties and Planning on the upcoming Verification exercise, outlining the instruments required for the Verification exercise.
|  | BANKING | Continuation of the Verification exercise of the ATMs, Note Counting and Bulk Niote Counting Machines. | To ensure accuracy and Compliance with WMD Act
|  | ELECTRICITY | Verification exercise of all metering instruments use for trade in the Electricity Sector | To ensure accuracy and Compliance with WMD Act
|  | MANUFACTURING | Verification exercise of all Weighing and Measuring instruments in the Manufacturing Sector of the economy. | To ensure accuracy and Compliance with WMD Act